## Sheet1
Sample adoption timeline
Citrix Workspace
| 15 - 13 weeks before rollout |  |  |  | 12 - 10 weeks before rollout |  |  |  | 8 weeks before rollout |  |  | 6 - 5 weeks before rollout |  |  |  | 2 weeks - 1 week before rollout
| Activities in this stage should begin during the procurement process or immediately after |  |  |  | During this stage, you will hold your kickoff meeting, develop your rollout timeline, and customize your adoption content |  |  |  | During this stage, you will develop your training plan and finalize all of your adoption content |  |  | During this stage, you will finalize training materials, begin implementing your communications, and train your end-user trainer |  |  |  | During this stage, you will roll out Citrix Workspace, train your end users, and ask for feedback
Line-of-Business Champion(s)
Implementation Lead
Technical Lead
Executive Champion
Success Lead
|  | • | • | • |  | • | • | • |  | • | • |  | • | • | • |  | • | •
|  | Get to know Citrix Workspace | Meet with IT | Build your team |  | Facilitate kickoff meeting | Create timeline | Customize your Communications strategy and tactics |  | Develop end-user training plan | Finalize communications tactics and timeline |  | Finalize end-user training plan materials | Implement communications strategy and tactics | Train the trainer |  | Train end-users | Ask for feedback
|  | Outcome: Educate yourself on what Citrix Workspace is and the benefits it will bring to users and the organization. Owner: Success Lead Other Participants: N/A Deadline: During the procurement process or immediately after | Outcome: Get any immediate questions you may have answered. E.g., primary outcomes for the organization, rollout timeline, preferences on level of participation in end-user adoption/communication efforts. Owner: Success Lead Other Participants: Technical Lead Deadline: During the procurement process or immediately after | Outcome: Complete the Project Team Template and send out an introduction email inviting prospective team members to a kickoff meeting. Owner: Success Lead Other Participants: N/A Deadline: During the procurement process or immediately after |  | Outcome: Get commitment from the team, generate excitement, and establish next steps (see sample kickoff meeting agenda below). Owner: Success Lead Other Participants: Executive Champion, Technical Lead, Implementation Lead, Line-of-Business Champion(s) Deadline: 12 weeks before rollout | Outcome: Using this sample timeline, establish the remaining portion through team collaboration Owner: Success Lead Other Participants: Implementation Lead (Incorporate the feedback of others as you see fit.) Deadline: Immediately following the kickoff meeting | Outcome: Using the samples provided in this adoption kit (emails, signage, end-user guide), customize your communications strategy to interest, excite, and educate your end-users. Owner: Implementation Lead Other Participants: Success Lead Deadline: 10 weeks before rollout |  | Outcome: Coordinate with HR or your learning and development team to develop a training plan in collaboration with line-of-business champions. Finalize schedule for line-of-business champions to facilitate training sessions. Owner: Implementation Lead Other Participants: Success Lead, Line-of-Business Champion(s) Deadline: 8 weeks before rollout | Outcome: All content has been customized to fit your organization’s needs, and everyone on your team is aware of responsibilities in implementation phase. Owner: Implementation Lead Other Participants: Executive Champion, Line-of-Business Champion(s) Deadline: 8 weeks before rollout |  | Outcome: Create supporting training materials as needed. Owner: Implementation Lead Other Participants: Line-of-Business Champion(s) Deadline: 6 weeks before rollout | Outcome: Ensure executive champion is equipped to make organization announcement. Ensure subsequent emails are scheduled to be sent. Ensure signage/office flyers are printed and ready for posting. Post all materials on the corporate intranet for easy access. Owner: Implementation Lead Other Participants: N/A Deadline: 6 weeks before rollout | Outcome: Facilitate “train the trainer” sessions to ensure assigned champions have opportunity to ask questions and become informed prior to leading training sessions. Owner: Success Lead Other Participants: Implementation Lead, Line-of-Business Champion(s) Deadline: 5 weeks before rollout |  | Outcome: Line-of-business champions to facilitate training sessions. Owner: Line-of-Business Champion(s) Other Participants: End-users Deadline: 2 weeks before rollout | Outcome: Check in with champions frequently. Ask for candid feedback from end-users. Owner: Success Lead Other Participants: Line-of-Business Champion(s) Deadline: 1 week before rollout